## CapEx Budget
CapEx Budget Template
Budget, commitments, and actuals in one place — the spreadsheet version of money truth. Replace the sample rows with your portfolio. Remaining = Committed − Actual.
Property | Project | Category | Budgeted | Committed | Actual | Remaining | Status
Cedar Ridge Apartments | Roof replacement — Bldg A/B | Roof | 42000 | 50000 | 0 |  | OPEN
Cedar Ridge Apartments | Unit turns — 2026 plan | Unit turns | 60000 | 31500 | 28900 |  | IN PROGRESS
Maple Court Townhomes | Parking lot resurface | Site work | 28000 | 26500 | 24800 |  | IN PROGRESS
Maple Court Townhomes | Boiler replacement | Mechanical | 18500 | 0 | 0 |  | PLANNED
Harbor View Flats | Hallway renovation (14 units) | Renovation | 96000 | 41000 | 12400 |  | IN PROGRESS
Harbor View Flats | Water heater replacements | Mechanical | 12800 | 9800 | 9800 |  | COMPLETE
TOTAL
Remaining = Committed − Actual. A negative Remaining means the project is over-committed — that is your early-warning signal. Status values: PLANNED, IN PROGRESS, COMPLETE, CANCELLED.