## Owner Report
Owner-Share Capital Report
Owner-ready project status in minutes, not a weekend. Fill in the property, owner, and period, then update the table from your budget tracker. Variance = Budgeted − Actual.
Property: | Cedar Ridge Apartments
Owner: | Sample Owner LP
Reporting period: | Q3 2026
Project | Budgeted | Committed | Actual | Variance | Status
Roof replacement — Bldg A/B | 42000 | 50000 | 0 |  | IN PROGRESS
Unit turns — 2026 plan | 60000 | 31500 | 28900 |  | IN PROGRESS
Parking lot resurface | 28000 | 26500 | 24800 |  | IN PROGRESS
TOTAL
Variance = Budgeted − Actual. Committed shows what is already promised to vendors — when Committed exceeds Budgeted, flag it in your note to the owner before they hear it elsewhere.